## Audit Action Plan
AUDIT ACTION PLAN 2015/2016 KAROO HOOGLAND MUNICIPALITY
Number | Page no | Finding | Classification | Rating | Priority | Preventative Control | 2015/2016 Financial Statements Actions | Official responsible | Implementation date | Due date | Progress %
Compliance
1 | 38 | COMP: Audit Committee did not review and report on compliance with SCM regulations. | Compliance | Other Matters | 2 | Inform Audit Committee of their functions and provide relevant information to Audit Committee Members | None | Muncipal Manager/ Internal Audit | 2017-01-03 | 2017-06-30 | 0%
2 | 42 | COMP: Local government procedures Audit Committee Meetings and Submission of Performance Management Report | Compliance | Other Matters | 2 | Inform Audit Committee of numbers of meetings per year and ensure performance management report is compiled and submitted in time. | None | Municipal Manager/Admin Manager | 2017-01-03 | 2017-03-31 | 50%
Employee costs
3 | 23 | EMP: Salary scales | Internal Control | Other Matters | 2 | Awaiting TASK process and engage with relevant officials | None | MM/CFO/HR Manager | 2017-01-03 | 2017-03-15 | 20%
4 | 53 | Employee Related Costs: No Employment contract and Performance agreement for a manager directly accountable to municipal manager | Internal Control | Other Matters | 2 | Employment Contract signed and Performance Contract signed | None | HR Manager | 2016-12-15 | 2016-12-31 | 100%
General IT controls
5 | 23 | Information technology governance- Service level agreements not monitored by management | Internal Control | Other Matters | 2 | Asset Manager to monitor SLA with Sebata. Compile monitoring register | None | Accountant BTO/ Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
6 | 29 | Information technology service continuity- No approved backup and retention strategy | Internal Control | Other Matters | 2 | Asset Manager to liase with Sebata for approved backup and retention strategy | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
7 | 28 | Program change management- No formal change request documentation completed | Internal Control | Other Matters | 2 | Asset Manager to ensure all changes must be documented. | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
8 | 28 | Program change management- No formally documented and approved processes in place to manage upgrades/updates made to all software | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
9 | 29 | Program change management-no evidence that vendors access is monitored | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
10 | 24 | Security management - No formally approved it security policy | Internal Control | Other Matters | 2 | Asset Manager to ensure that such a policy is developed and implemented | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
11 | 27 | User access control- No processes in place for independent reviews of the activities of the person responsible for granting user access. | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy. Develop and implement Acces Control Request form. | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
12 | 25 | User access control-No formal access request documentation being completed for registering users, changing access rights, passwords etc | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy. Develop and implement Access Control Request form. | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
13 | 25 | User access control-No formally documented and approved process that is used to manage the process of granting users access to modules | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy. Develop and implement Acces Control Request form. | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
14 | 26 | User access control-No processes in place to ensure that users’ access and privileges on all financial systems are periodical reveiwed. | Internal Control | Other Matters | 2 | Asset Manager to ensure that these processes are documented in the IT Policy. Review access control on quarterly basis | None | Accountant Assets | 2016-12-15 | 2017-02-28 | 50%
Internal Control
15 | 32 | Business conducted with deregistered companies | Internal Control | Other Matters | 2 | Do CIPRO search before conducting business to ensure the Municipality do not do business with deregistered companies | None | Accountant SCM | 2017-02-28 | 2017-06-30 | 80%
16 | 30 | Inadequate controls to prevent electricity loses | Internal Control | Other Matters | 2 | Unscheduled meter inspections to be conducted througout the financial year. | None | Accountant Assets/ Director Technical Services | 2017-02-28 | 2017-06-30 | 50%
17 | 33 | Internal Control: Entity Level Controls 1) The code of conduct is not periodically acknowledged by signature from all employees. 2) Not all policies and procedures have been approved 3) There are no documented policies which state that overriding of internal control by low-level management personnel is prohibited except in emergency situations, and if it happens, upper-level management are immediately notified and the circumstances documented. 4) There is no evidence that compensation and promotion is based on achievements and performance. 5) There is no evidence management takes quick and appropriate action as soon as there are any signs that a problem may exist. 6) There is no evidence that management takes action when there are violations of policies, procedures, or the code(s) of conduct. 7) There are no processes in place to prevent management override of controls 8) Employees are not provided with candid and constructive job performance counselling. 9) There are no performance appraisals. These should be based on an assessment of critical job factors and clearly identify areas in which the employee is performing well and areas that need improvement. 10) There is no evidence that there is an appropriate training programme that meets the needs of all employees. 11) Supervisors have not been trained to provide effective job performance counselling. 12) The staffing structure is not adequate for proper performance management and measurement. 13) Management has not put processes in place to ensure that authority, responsibility and accountability is clearly assigned throughout the organisation and is clearly communicated to all employees, including for the under-mentioned performance management areas: (i) Developing and evaluating output performance measures (ii) Monitoring and managing data measurement and reporting processes (iii) Reporting sufficient and appropriate information to stakeholders 14) There are no documented processes for performance evaluation which contain specific references to internal control-related duties, responsibilities, and accountability. 15) Promotion, compensation, and rotation of employees is based on periodic performance appraisals. 16) Performance areas in the contract are linked to the objectives, indicators and targets in the entity's strategic plan. 17) The importance of integrity and ethical values are reflected in the performance appraisal criteria. 18) Employees are provided with appropriate feedback and counselling on their job performance and suggestions for improvements. 19) Candidates who change jobs often are given particularly close attention. 20) Hiring standards require investigations for criminal records for all potential employees. 21) There is no evidence that the municipality clearly communicates its objectives, indicators and targets to all employees, and does management obtain feedback signifying that the communication has been effective. 22) There is no evidence that consideration is given to possible risks resulting from the lack of qualifications of personnel hired or the extent to which they have been trained or not trained. 23) There is no evidence that risks resulting from unusual employee access to vulnerable assets are considered. 24) Management’s strategy does not provide for routine feedback and monitoring of performance and control objectives. | Internal Control | Other Matters | 2 | See detailed Internal Control Sheet | None | MM/ CFO/ Admin Manager/ Director Technical Services/ Community Services Manager/ HR Manager | 2017-02-28 | 2017-04-30 | 0%
18 | 39 | Non-compliance: Roles and responsibilities of audit committee and internal audit unit | Compliance | Other Matters | 2 | Inform Audit Committee and Internal Audit of their functions and provide relevant information. | None | MM/CFO/Admin Manager/Internal Audit | 2017-01-03 | 2017-06-30 | 50%
19 | 31 | Policies and procedures The municipality did not have the following approved policies and documents in place during the period under review: 1) Fraud prevention plan 2) IT security policy 3) Risk management Strategy | Internal Control | Other Matters | 2 | Develop and Implemented 1,2 and 3 | None | MM/CFO/Admin Manager/ Accountant Assets | 2017-01-03 | 2017-03-31 | 60%
20 | 64 | Procurement: No measures to monitor contract performance | Compliance | Other Matters | 2 | Obtain all register and contracts from various officials and compile different registers. Manage income and expenses on monthly basis | None | Accountant BTO | 2017-01-03 | 2017-03-31 | 60%
21 | 32 | Various policies not approved and others not reviewed during the year The municipality currently uses draft policies and procedures as the policies have not been approved by council. The following serves as examples; 1) Indengent Policy 2) Office hours policy 3) Archive & Registry policy 4) Bank facilities and checks approval 5) HIV policy 6) Internet policy 7) Cell phone policy | Internal Control | Other Matters | 2 | Ensure these policies are develop,approved,reviewed and implemented on yearly basis. Ensure Council resolution for all policies. | None | MM/CFO/All Accountants/Admin Manager/Director Technical Services/ Community Services Manager/Admin Manager | 2017-01-03 | 2017-03-31 | 50%
Compliance
22 | 36 | Compliance: No reports relating to unauthorised,irregular, fruitless and wasteful expenditure We noted that reports relating to unauthorised, irregular, fruitless and wasteful expenditure were not submitted to the mayor, MEC for local government and the Auditor-General. | Compliance | Other Matters | 2 | Ensure that reports for irregular,fruitless and wastefull expenditure are submitted to mayor,MEC and AG as per Section 32 of the MFMA | None | Accountant SCM/ Admin Manager/CFO/Municipal Manager | 2017-01-03 | 2017-06-30 | 0%
23 | 36 | No risk assessment performed during the year | Compliance | Other Matters | 2 | Risk Assesment was done during December 2016 and awaiting final report from PT | None | MM/CFO/All relevant Directors & Managers of Dept's to review their Departments Risks | 2016-12-15 | 2017-02-28 | 80%
24 | 41 | Non compliance: Audit committee meetings and submission of audit report on performance management | Compliance | Other Matters | 2 | Inform Audit Committee of numbers of meetings per year and ensure performance management report is compiled and submitted in time. | None | Municipal Manager/Admin Manager | 2016-12-15 | 2017-03-31 | 60%
25 | 40 | Non-compliance: No audit committee charter and evidence of appointment of audit committee by the council | Compliance | Other Matters | 2 | Charter was developed and appointment letters were signed. | None | Internal Audit / Municipal Manager | 2016-12-15 | 2017-03-31 | 60%
26 | 5 | Non-compliance- Section 62 (1)(d)-MFMA-Unauthorised, irregular, fruitless and wasteful expenditure | Compliance | Audit Report | 1 | Obtain lists of different expenditures for the past 3 years. Investigate each and make a comment to each expenditure for submission to Section 32 Committees. | None | CFO/Accountant SCM | 2016-12-15 | 2017-03-31 | 30%
27 | 42 | Roll over of Library Services Grant | Compliance | Other Matters | 2 | Obtain support from the Department | None | Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
Compliance
28 | 65 | Road maintenance | Service delivery | Other Matters | 2 | Ensure plan develop and implemented | None | Director Technical Services | 2016-12-15 | 2017-03-31 | 0%
29 | 66 | Water Infrastructure Maintenance | Service delivery | Other Matters | 2 | Ensure plan develop and implemented | None | Director Technical Services | 2016-12-15 | 2017-03-31 | 0%
Procurement
30 | 8 | Procurement - The preference point system was not applied in the procurement of goods and services above R30 000 | Misstatement | Audit Report | 1 | Work through entire population for 2014/2015 and 2015/2016 and ensure PPPFA points are calculated | If applicable adjust irregular expenses disclosure on AFS comparitive with the compilation of the 2016/2017 AFS | Accountant SCM | 2016-12-15 | 2017-03-31 | 50%
31 | 6 | Procurement: Goods and services not procured through competitive bidding | Misstatement | Audit Report | 1 | Work through entire population for 2014/2015 and 2015/2016 and ensure PPPFA points are calculated | If applicable adjust irregular expenses disclosure on AFS comparitive with the compilation of the 2016/2017 AFS | Accountant SCM | 2016-12-15 | 2017-03-31 | 50%
32 | 7 | Procurement: Non-compliance with SCM Regulations a) The winning provider did not submit an original/valid certified-copy of tax clearance certificate and; b) Winning provider did not submit a declaration of interest Note: All the above awards were not advertised for at least seven (7) days on the website and official notice board of the municipality as required by SCM regulation 18(a). | Misstatement | Audit Report | 1 | Obtain declarations of interest from all vendors. Advertise for at least 7 days on notice boards and website. Obtain valid tax clearances for all vendors | If applicable adjust irregular expenses disclosure on AFS comparitive with the compilation of the 2016/2017 AFS | Accountant SCM | 2016-12-15 | 2017-03-31 | 50%
Immovable assets
33 | 50 | PPE-Differences between detailed WIP schedule and AFS/Register | Misstatement | Other Matters | 2 | Identify all differences and correct WIP schedule and Asset Register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
34 | 12 | PPE: Asset which could not be traced to the asset register | Misstatement | Audit Report | 1 | Identify these assets and include in Asset Register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
35 | 46 | PPE: Assets incorrectly classified as disposed | Misstatement | Other Matters | 2 | Identify all these assets and correct Asset Register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
36 | 48 | PPE: Assets not recorded in the asset register | Misstatement | Other Matters | 2 | Identify all these assets and correct Asset Register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
37 | 49 | PPE: Description as per asset register differs from the actual asset verified | Misstatement | Other Matters | 2 | Correct descriptions of assets on Asset register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
38 | 16 | PPE: Land and buildings not in the name of the municipality were recorded in the asset register | Misstatement | Audit Report | 1 | Identify these assets and remove from Asset Register | Adjust AFS 2016/2017 if applicable | Accountant Assets/ Accountant Revenue | 2016-12-15 | 2017-03-31
39 | 14 | PPE: No sufficient evidence to confirm if assets were properly assessed for impairment | Misstatement | Audit Report | 1 | At year end with the asset verification assess all assets conditions for an accuarte calculation of impairment | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-06-30 | 0%
40 | 19 | PPE: Prior period error adjustments Appropriate supporting documentation could not be obtained for restatements made in the period under review. | Misstatement | Audit Report | 1 | Obtain appropriate evidence | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
41 | 9 | PPE: Property plant and equipment not physically verified | Misstatement | Audit Report | 1 | Obtain co-ordinates for Assets not verified. | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
42 | 43 | PPE: Control findings -Fixed asset register 1. 56 Assets have got no purchases cost 2. 496 assets have got no physical location. 3. 3468 assets have no depreciation method used. 4. 5 assets have got no bar code. 5. 1124 assets have got duplicated bar codes. 6. 114 assets disposed have got no disposal date. 7. 114 assets disposed have got no disposal amount column. 8. 15 assets have got asset condition. 9. No monthly reconciliations were done between the asset register and the general ledger. | Internal Control | Other Matters | 2 | Correct Asset register and compile asset reconciliation on monthly basis | None | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
43 | 45 | PPE: Differences between the asset register and AFS | Misstatement | Audit Report | 1 | Identify the differences and correct both asset register and AFS | Adjust AFS 2016/2017 if applicable | Accountant Assets/ Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
Investment property
45 | 51 | Investment property: Assets which could not be physically verified | Misstatement | Other Matters | 2 | Obtain co-ordinates for Assets not verified. | None | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
46 | 18 | Investment property: Incomplete investment register | Misstatement | Audit Report | 1 | Update Investment Register | Adjust AFS 2016/2017 if applicable | Accountant Assets | 2016-12-15 | 2017-03-31 | 0%
Movable assets
47 | 52 | PPE: Assets not adequately insured | Internal Control | Other Matters | 2 | Obtain quotations for inclusion of all assets on the Insurance portfolio | None | Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
48 | 52 | PPE: Incomplete lease asset register. | Internal Control | Other Matters | 2 | Ensure that the assets are returned to the lessor. | None | Accountant BTO/ Accountant SCM | 2016-12-15 | 2017-03-31 | 0%
Operating expenditure
49 | 56 | Audit fees: Incorrect journal entry | Misstatement | Other Matters | 2 | Pass correction journal | Adjust AFS 2016/2017 if applicable | Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
50 | 57 | Expenditure: Payments not made within 30 days of invoice | Misstatement | Other Matters | 2 | Ensure that payments to creditors are within 30 days of invoice | None | Accountant SCM | 2016-12-15 | 2017-06-30 | 0%
Revenue
51 | 61 | Revenue:Understatement of interest on outstanding debtors | Misstatement | Other Matters | 2 | Test system calculated interest by means of manual calculations. Adjust policy if applicable. | Adjust AFS 2016/2017 if applicable | Accountant Revenue | 2016-12-15 | 2017-04-30 | 0%
Payables
52 | 58 | Creditors: Sub ledger does not agree to the general ledger | Misstatement | Other Matters | 2 | Ensure that sub-ledger balance with General Ledger. Compile monthly recons. | Was adjusted with adjusted AFS 2015/2016 | Accountant BTO Accountant SCM | 2016-12-15 | 2017-02-28 | 90%
53 | 58 | Library Services Grant not backed by cash reserves | Compliance | Other Matters | 2 | Also see number 24. Correct Grant if no support can be obtained. | Was adjusted with adjusted AFS 2015/2016 | Accountant BTO | 2016-12-15 | 2017-04-30 | 0%
54 | 59 | Payable : Prior period error disclosure | Compliance | Other Matters | 2 | AFS 2015/2016 was adjusted. The retension was removed from payables and disclosed as retensions. | None | Accountant BTO | 2016-10-27 | 2016-10-27 | 100%
Predetermined objectives
55 | 21 | AOPO – IDP,SDBIP and Annual Performance Report | Performance Report | Audit Report | 1 | With the implementation of mSCOA the new EMS will cater for a fully integrated PMS. Ensure that all information is correctly captyred on EMS. Manual IDP,SDBIP an Annual Performance report to be submitted to Auditors | None | Community Service Manager/ HR Manager / Admin Manager/ Technical Manager/ CFO/ MM | 2016-12-15 | 2017-05-31 | 0%
56 | 20 | No performance management system (PMS) established | Performance Report | Audit Report | 1 | With the implementation of mSCOA the new EMS will cater for a fully integrated PMS. Ensure that all information is correctly captyred on EMS | None | Community Service Manager/ HR Manager / Admin Manager/ Technical Manager/ CFO/ MM | 2016-12-15 | 2017-05-31 | 0%
Provisions
57 | 60 | Landfill site permits | Compliance | Other Matters | 2 | Obtain licence for outstanding landfill site | None | Director Technical Services | 2016-12-15 | 2017-06-30 | 50%
Taxes
58 | 62 | Value added tax: Misstatement of input vat accrual account | Misstatement | Other Matters | 2 | The credit side of the journal (GL no: 7801/7804/7803) which is input vat actual account is correct as its reducing this account after the amount claimed is received from SARS. Therefore the correct debit account should have been affected in general ledger account no: 0020/0814/0000 which offsets the entire amount actual claimed from SARS. Pass correction Journal. | Adjust AFS 2016/2017 if applicable | Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
59 | 63 | Value Added Tax: Output vat reconciling items not explained The evidence provided for finding 1 relating to reconciling items. For finding 2 and 3 the supporting calculation don’t add up to the differences raised as exceptions | Misstatement | Other Matters | 2 | Document explanations for reconcilaing items. Re-do calculations as per exceptions and ensure it ties up. | Adjust AFS 2016/2017 if applicable | Accountant BTO | 2016-12-15 | 2017-03-31 | 0%
___________________________________________
Municipal Manager: GW von Möllendorf

## Internal Control (17)
Number | Page no | Finding | Classification | Rating | Priority | Preventative Control | 2016/2017 Financial Statements Actions | Official responsible | Implementation date | Due date | Progress %
17 | 33 | 1) The code of conduct is not periodically acknowledged by signature from all employees. | Internal Control | Other Matters | 2 | Communicate Code of Conduct to employees on annualy basis | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 2) Not all policies and procedures have been approved | Internal Control | Other Matters | 2 | Get all policies approved | None | MM/ Admin Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 3) There are no documented policies which state that overriding of internal control by low-level management personnel is prohibited except in emergency situations,and if it happens, upper-level management are immediately notified and the circumstances documented. | Internal Control | Other Matters | 2 | Develop Policy | None | MM/ Admin Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 4) There is no evidence that compensation and promotion is based on achievements and performance | Internal Control | Other Matters | 2 | Compensation equals Performance !! Legal Matter | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 5) There is no evidence management takes quick and appropriate action as soon as there are any signs that a problem may exist. | Internal Control | Other Matters | 2 | Document Processes followed | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 6) There is no evidence that management takes action when there are violations of policies, procedures, or the code(s) of conduct. | Internal Control | Other Matters | 2 | Document Processes followed | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 7) There are no processes in place to prevent management override of controls | Internal Control | Other Matters | 2 | Develop processes | None | MM/ Admin Manager/ CFO | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 8) Employees are not provided with candid and constructive job performance counsilling | Internal Control | Other Matters | 2 | Give Counsilling to Employees | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 9) There are no performance appraisals. These should be based on an assessment of critical job factors and clearly identify areas in which the employee is performing well and areas that need improvement | Internal Control | Other Matters | 2 | Develop Performance Appraisals Legal Matter | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 10) There is no evidence that there is an appropriate training programme that meets the needs of all employees | Internal Control | Other Matters | 2 | Conclude WSP | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 11) Supervisors have not been trained to provide effective job performance counselling. | Internal Control | Other Matters | 2 | Supervisors to undergo training | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 12) The staffing structure is not adequate for proper performance management and measurement | Internal Control | Other Matters | 2 | Adjust structure | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 13) Management has not put processes in place to ensure that authority, responsibility and accountability is clearly assigned throughout the organisation and is clearly communicated to all employees, including for the under-mentioned (i) Developing and evaluating output performance measures (ii) Monitoring and managing data measurement and reporting processes (iii) Reporting sufficient and appropriate information to stakeholders | Internal Control | Other Matters | 2 | See (i),(ii) and (iii) | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 14) There are no documented processes for performance evaluation which contain specific references to internal control-related duties, responsibilities, and accountability. | Internal Control | Other Matters | 2 | Develop processes | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 15) Promotion, compensation, and rotation of employees is based on periodic performance appraisals. | Internal Control | Other Matters | 2 | Ensure this | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 16) Performance areas in the contract are linked to the objectives, indicators and targets in the entity's strategic plan. | Internal Control | Other Matters | 2 | Ensure this | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 17) The importance of integrity and ethical values are reflected in the performance appraisal criteria. | Internal Control | Other Matters | 2 | Ensure this | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 18) Employees are provided with appropriate feedback and counselling on their job performance and suggestions for improvements. | Internal Control | Other Matters | 2 | Ensure this | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 19) Candidates who change jobs often are given particularly close attention. | Internal Control | Other Matters | 2 | Ensure this | None | H/R Manager | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 20) Hiring standards require investigations for criminal records for all potential employees. | Internal Control | Other Matters | 2 | Implement criminal record checks | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 21) There is no evidence that the municipality clearly communicates its objectives, indicators and targets to all employees, and does management obtain feedback signifying that the communication has been effective. | Internal Control | Other Matters | 2 | Obtain such evidence | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 22) There is no evidence that consideration is given to possible risks resulting from the lack of qualifications of personnel hired or the extent to which they have been trained or not trained. | Internal Control | Other Matters | 2 | Obtain such evidence | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 23) There is no evidence that risks resulting from unusual employee access to vulnerable assets are considered. | Internal Control | Other Matters | 2 | Obtain such evidence | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%
17 | 33 | 24) Management’s strategy does not provide for routine feedback and monitoring of performance and control objectives. | Internal Control | Other Matters | 2 | Develop feedback strategy | None | H/R Manager/ MM | 2017-02-28 | 2017-04-30 | 0%